## GEO 30-Day Master Checklist
GEO 30-Day Master Checklist · Consolidated from all team inputs · v2 (Complete)
GO MO Group ¦ Internal Execution Guide ¦ Post-Sale Month 1 · Synthesised from: Bez · Kris · Amisha · Jonathan · Avichal · Roshni · Vishnu
Phase | Day Target | # | Category | Task | How to Execute (Step-by-Step) | Tool(s) | Dependency / Notes | Owner | Training Req? | Quick Win? | Status
PHASE 1 Days 1–5 Foundation & Access
P1 | Day 1 | 1 | Setup & Access | Align internal team on GEO scope, objectives, and deliverables — distribute a 1-page project brief | 1. CSM creates a Google Doc titled 'GEO Project Brief – [Client Name]'. Include: client name · project start date · 30/60/90-day deliverable list · each team member's role (SEO lead, content, analytics, client services) · a 'What GEO is / is not' section (2–3 sentences max). 2. Share brief via Basecamp 24 hrs BEFORE the kick-off meeting — not during. Subject: '[Client] GEO Kick-off – Please Read Before [Date]'. 3. Request read-receipt or ✅ emoji reply from every recipient. 4. Hold a 60–90 min internal kick-off in Google Meet. Invite: SEO lead · content lead · analytics · social · client services. 5. Fill in a RACI table (Responsible / Accountable / Consulted / Informed) for each workstream: Workstream ¦ Responsible ¦ Accountable ¦ Consulted ¦ Informed Save RACI in Google Drive project folder. DONE WHEN: Brief acknowledged by 100% of team. RACI saved and shared. | Google Meet · Google Docs · Basecamp | No prior steps | CSM | No | No | To Do
P1 | Day 1 | 2 | Setup & Access | Build stakeholder map and confirm ownership + approval workflow per workstream | 1. Open a new Google Sheet tab titled 'Stakeholder Map'. Columns: Name ¦ Department ¦ Role on this project ¦ Email ¦ Slack handle 2. Fill in all known names. Leave blanks for unknowns. 3. Circulate to manager to validate and fill gaps. 4. Mark sheet as 'v1 – confirmed [date]'. 5. For each workstream, name ONE person per role in a separate table: Workstream ¦ Delivery Owner ¦ Approver ¦ Implementation Owner ¦ Reporting Owner 6. Share the table in Slack or email. Ask each person to reply 'Confirmed'. 7. Screenshot or copy confirmations into the project doc. DONE WHEN: Stakeholder map has zero blank rows. Every workstream has a named person per role with written confirmation. | Google Sheets · Slack · Basecamp | Depends on task 1 | CSM | No | No | To Do
P1 | Day 1 | 3 | Setup & Access | Create GEO working folder structure in Google Drive and Basecamp | GOOGLE DRIVE: 1. Create top-level folder: [Client Name] – GEO – [Month YYYY] Sub-folders: 00_Admin 01_Strategy 02_Technical_Audit 03_Content_Audit 04_Schema 05_GEO_Readiness 06_AI_Benchmarking (sub-folders: Day-1-Baseline / Monthly-Snapshots) 07_Brand_Narrative 08_Trust_Proof 09_Reporting 10_Client_Deliverables 2. Share top-level folder: Edit access for team. View access for client (unless agreed otherwise). BASECAMP: 3. Create a matching Basecamp project with same folder structure. 4. Add all team members with correct permissions. 5. Pin Drive link in Basecamp. ALSO CHECK: 6. Confirm CRM / lead database access is available (not just web analytics). 7. Cross-check which tools were accessed during the audit vs what access exists now. Flag gaps. DONE WHEN: Drive folder live. Basecamp project active. All team added. Drive link pinned. | Google Drive · Basecamp | Depends on task 2 | CSM + Analyst | No | No | To Do
P1 | Day 1 | 4 | Setup & Access | Align team on reporting cadence, internal review cadence, and 90-day working model | Run a 30-min internal team meeting (separate from kick-off): Title: 'GEO [Client] – Working Model Alignment' Agenda items to decide and document: · Reporting day (client-facing delivery) · Internal review day/time (who reviews before client sees) · Client sync day/time (biweekly) · Weekly internal check-in day/time (30 min — separate from client syncs) · Tool stack confirmed for this client · Who has final approval before client delivery Save meeting notes to 00_Admin. Pin as Basecamp note with names next to each decision. DONE WHEN: All cadence decisions confirmed and pinned in Basecamp. Zero unowned decisions. | Google Calendar · Basecamp | Depends on task 1 | CSM | No | No | To Do
P1 | Days 1–2 | 5 | Setup & Access | Send client access questionnaire and book weekly internal + biweekly client syncs | ACCESS QUESTIONNAIRE: 1. Prepare a Google Sheet credentials template. Rows for every tool: GA4 ¦ GSC ¦ Bing Webmaster Tools ¦ GTM ¦ CMS (specify platform) ¦ Hosting/CDN ¦ Schema plugin ¦ Screaming Frog / SEMrush ¦ YouTube Studio ¦ GBP ¦ Reddit ¦ Trustpilot ¦ G2 ¦ Capterra ¦ Social accounts 2. For each platform, pre-fill the exact team email address the client should grant access to. 3. Send via email: '[Client] – Access Request for GEO Project'. Give 48-hour response deadline. 4. Log in Basecamp. Move completed sheet to 00_Admin. CALENDAR: 5. Create recurring Google Calendar event: '[Client] GEO Biweekly Sync' — every 2 weeks, 13 occurrences. Attach standing agenda: Actions from last meeting → Progress update → This week's priorities → Blockers → Questions 6. Create weekly internal check-in (30 min) for delivery team — separate from client syncs. Day/time: [agree in task 4 meeting] DONE WHEN: Questionnaire sent. 13 biweekly client invites accepted. Weekly internal sync in calendar. | Google Sheets · Email template · Google Calendar | Depends on task 4 | CSM | No | No | To Do
P1 | Days 1–2 | 6 | Setup & Access | Verify access to all analytics, technical, and CMS platforms — log in Access Log | CREATE ACCESS LOG: Open a new Google Sheet tab 'Access Log'. Columns: Platform ¦ URL/Login Link ¦ Access Level ¦ Date Confirmed ¦ Status (✅/❌) ¦ Blocker Notes VERIFY EACH PLATFORM: · GA4: Admin → Data Streams → green status. Open Realtime + visit site → you should appear instantly. · GSC: Confirm property matches canonical domain (https:// version). Check 3+ months of data loads. · Bing Webmaster Tools (DO NOT SKIP — surfaces AI performance data): Log in at bing.com/webmasters. If not set up: verify via XML file or meta tag. Navigate to 'AI Performance' report. Screenshot baseline data. · GTM: Confirm correct container loads. Check for duplicate tags or consent mode issues. · CMS: Confirm you can view AND edit pages (not just view). · Hosting/CDN: Confirm access to server config / CDN settings. · Schema plugin (Yoast / RankMath / Schema Pro): confirm installed and accessible. · Screaming Frog: licence valid. · SEMrush: confirm account has access to client project. FLAG IMMEDIATELY: · Any 2FA or permission issues · Platforms where access level is lower than needed (e.g. View only when Edit needed) · For any ❌: log the specific error + person responsible for resolving it DONE WHEN: ✅ on all platforms or documented escalation path for each ❌. | GA4 · GSC · Bing WMT · GTM · CMS · Screaming Frog · SEMrush | Depends on task 5 | Analyst | Yes — Bing WMT AI report setup | No | To Do
P1 | Days 1–2 | 7 | Setup & Access | Verify access to YouTube, social, review platforms, and GBP — flag creation tasks | ADD TO ACCESS LOG (same sheet as task 6): Platforms to check: YouTube Studio ¦ LinkedIn ¦ Facebook ¦ Instagram ¦ Twitter/X ¦ Reddit ¦ GBP ¦ Trustpilot ¦ G2 ¦ Capterra ¦ Clutch ¦ Yelp ¦ any sector-specific review platforms FOR EACH PLATFORM: mark ✅ or ❌ with blocker notes. IF PLATFORMS DO NOT EXIST: · YouTube channel missing → flag as creation task (not just access task) · No Trustpilot profile → do NOT default to creating one. First check which review platforms include brand reviews (run brand mentions search first — task 38). Create only on high-influence platforms. · Request a @clientcompany email ID: team will use it to create accounts where needed. DONE WHEN: All social/review platform rows in Access Log confirmed with status. | GBP · YouTube Studio · Trustpilot · G2 · Capterra · Clutch | Depends on task 5 | CSM + Analyst | No | No | To Do
P1 | Day 2 | 8 | Setup & Access | Create Blockers Log — assign owner and resolution date for every outstanding item | 1. Add a tab 'Blockers Log' to the Access Log Google Sheet. Columns: Blocker Description ¦ Platform ¦ Impact if Unresolved ¦ Owner ¦ Target Resolution Date ¦ Status 2. Copy every ❌ from the Access Log into this tab immediately. 3. Assign an owner (internal or client) and a specific resolution date for every blocker. 4. Share with account manager. 5. Flag in Basecamp which tasks in Days 5+ CANNOT START until each blocker is resolved. 6. Send follow-up email for any unresolved items with a hard deadline. DONE WHEN: Zero unowned blockers. Every item has an owner, date, and impact note. | Google Sheets · Basecamp · Email | Depends on tasks 6–7 | CSM | No | No | To Do
P1 | Days 1–2 | 9 | Pre-Kickoff Check | Verify whether a GEO Audit exists and whether it needs refreshing before proceeding | CSM reviews Google Drive for an existing GEO Audit document. IF NO AUDIT EXISTS: · Flag to delivery lead immediately — an audit must be completed before proceeding. · Do not start strategy tasks until audit is confirmed. IF AUDIT IS LESS THAN 2 MONTHS OLD: · Treat as valid input. Proceed. IF AUDIT IS MORE THAN 2 MONTHS OLD: · Note which sections need refreshing: - Entity data (company details, schema accuracy) - AI snapshot (which LLMs cite the brand and how) - Competitor citations (who appears now vs when audit was done) · Log as Basecamp to-do with assigned owner before team proceeds. DONE WHEN: Audit status confirmed and action flagged if needed. | Google Drive · Basecamp | Depends on task 3 | CSM | No | No | To Do
PHASE 2 Days 2–14 Audit & Baseline
P2 | Days 2–5 | 10 | Strategic Alignment | Run client kickoff — capture business goals, audience, markets, and 90-day success definition | BEFORE THE CALL (24 hrs prior): · Send kickoff agenda Google Doc to client. · Send prep email: 'We have booked the meeting — please prepare the following and bring all relevant stakeholders.' · Ask client to have ready: primary business goal · top services/products · buyer personas · buying questions · target geos and languages · definition of success. THE CALL (90 min): · RECORD THE CALL. · Confirm project goal, timeline, and scope (10 min). · Document answers to: - Most important business goal in 90 days? (leads / revenue / awareness) - Top 2–3 most valuable services or products? - Primary buyer — who are they? What pain do they feel before finding this company? - What questions do buyers ask before purchasing? - Target geographies and languages? - Any compliance, legal, or messaging restrictions? Claims that need approval? - What does success look like at Day 30 / 60 / 90? - Primary conversion actions (purchase / get-a-quote / contact / demo / download)? AFTER THE CALL (within 24 hrs): · Clean up notes. Send to client for sign-off via email. · Save confirmed doc in /01_Strategy. DONE WHEN: Client has confirmed the summary doc in writing. | Google Meet · Google Docs (kickoff agenda template) | Depends on task 8 | CSM | No | No | To Do
P2 | Days 2–5 | 11 | Strategic Alignment | Identify primary audience segments, pain points, and key branded/non-branded themes | 1. Analyst reviews existing client materials: past briefs · personas · previous audits. 2. In kickoff (task 10): ask client to come prepared with answers. 3. Draft audience segment map with these fields per segment: Segment Name ¦ Core Pain Points ¦ Buying Questions ¦ Decision Triggers ¦ Branded Search Themes ¦ Non-Branded Search Themes 4. Share with CSM for review. Save in /01_Strategy. Note: Do NOT duplicate Brand Narrative section. This is about buyer behaviour, not brand language. | Google Docs · kickoff notes | Depends on task 10 | Analyst | No | No | To Do
P2 | Days 2–5 | 12 | Strategic Alignment | Confirm target markets, geographies, languages, compliance restrictions, and messaging rules | Covered in kickoff (task 10). Separately confirm: · All target countries and regions · Languages the site operates in · Any compliance or regulatory restrictions (healthcare, finance, legal) · Specific claims that require legal/compliance approval before publishing — flag these in red in the Brand Brief doc CSM confirms in kickoff or via follow-up email. Analyst logs confirmed details in /01_Strategy folder. | Kickoff notes · Google Docs | Depends on task 10 | CSM + Analyst | No | No | To Do
P2 | Days 2–5 | 13 | Strategic Alignment | Identify key competitors in both organic search AND AI answer environments | AI COMPETITORS: 1. Analyst runs manual prompt tests in ChatGPT and Perplexity for 3–5 category queries: e.g. 'Best [service category] for [audience]' · 'Top [service] companies for [use case]' 2. Log every brand that appears consistently across 2+ AI tools — these are the AI competitors. ORGANIC COMPETITORS: 3. Search client's 3 main keywords in Google. Note page 1 rankings. 4. Cross-reference with SEMrush competitor overview. COMBINED: 5. Merge into a shortlist of 5–8 competitors. For each, note: what they claim to do · who they serve · proof they show · how they appear in AI answers. Save competitor shortlist in /01_Strategy. | ChatGPT · Perplexity · Google Search · SEMrush | Depends on task 10 | Analyst | No | No | To Do
P2 | Days 2–5 | 14 | Strategic Alignment | Document differentiators, proof points, sensitive claims, and messaging needing approval | CSM leads client session (in kickoff or dedicated follow-up call). Create a differentiator table: Claim ¦ Supporting Proof ¦ Approved to use? (Yes / Needs sign-off / Do not use) For any regulatory-sensitive claims (healthcare, finance, legal): · Flag in red in the table · Create a Basecamp to-do for compliance review before that claim is used Analyst formats into Brand Source-of-Truth doc (see task 33). DONE WHEN: Differentiator table complete with approval status on every claim. | Google Docs · Brand brief template | Depends on tasks 10–13 | CSM + Analyst | No | No | To Do
P2 | Day 3 | 15 | Strategic Alignment | GEO ambition assessment — Leader (broad category visibility) or Focused (high-value terms) | CSM facilitates 15-min discussion with client in kickoff or standalone call. Present two clear options: · LEADER — appear across broad category questions. Harder, longer timeline, requires comprehensive content coverage. · FOCUSED — appear for specific high-value queries. Faster wins, more targeted effort. Document the decision in /01_Strategy. This determines prompt set scope and Month 2 priorities. DONE WHEN: Ambition level agreed and documented with client. | Kickoff agenda · Google Docs | Depends on task 10 | CSM | No | No | To Do
P2 | Days 3–4 | 16 | Strategic Alignment | Define target prompt set of 10–20 natural-language queries — all 5 types required | Analyst drafts prompt set in Google Sheets. SHEET COLUMNS: Prompt ¦ Type ¦ Platform to Test ¦ Priority ¦ Market/Language/Device Assumption ¦ Frequency (monthly/biweekly) ¦ Evidence Format REQUIRED PROMPT TYPES (at least 2 per type): · Branded: 'Tell me about [Company Name]' · Non-branded category: 'Who are the best [service] providers for [audience]?' · Problem-solution: 'How do I solve [key pain point]?' · Comparison: 'What is the difference between [Client] and [Competitor]?' · '[Client] vs [Competitor]' · Buyer-intent: 'Best [service category] for [audience/situation]' EVIDENCE FORMAT TO DOCUMENT PER PROMPT: · Screenshots · Citations · Answer text · Competitors mentioned · Source URLs SCORING RULES (define before running): · Brand Presence (Y/N) · Position in response (mentioned first / middle / end / not mentioned) · Sentiment (positive / neutral / negative) · Accuracy vs brand SOT · Citation quality (own site / third party / none) REPEATABILITY NOTE: LLM answers vary — do not overclaim precision. Track trends over time, not single data points. Market/language/device assumptions: document explicitly (e.g. 'English language, UK market, desktop'). CSM routes to client for sign-off before running. DONE WHEN: Prompt set covers all 5 types. Assumptions documented. Ready for client sign-off. | Google Sheets · Kickoff notes | Depends on task 15 | Analyst | Yes — prompt-building guide/recording needed | No | To Do
P2 | Days 4–5 | 17 | Strategic Alignment | Run every prompt across all 5 LLMs, record baseline results, and archive all evidence | TRACKING SHEET COLUMNS (one row per prompt × tool): Prompt ¦ AI Tool ¦ Brand Appears? (Y/N) ¦ Exact Description Used ¦ Cited URLs ¦ Competitors Mentioned ¦ Response Format (list/prose/table/none) ¦ Platform-Specific Notes PLATFORMS TO TEST (all 5): ChatGPT (GPT-4o) · Gemini Advanced · Perplexity · Claude · Bing Copilot FOR EACH PROMPT × TOOL: 1. Open AI tool in fresh browser tab (not cached session). 2. Paste prompt exactly. Do not rephrase. 3. Fill in all tracking sheet columns. 4. Take a full-page screenshot immediately. Save to: /06_AI_Benchmarking/Day-1-Baseline/[Platform]/[Prompt-slug]_[YYYY-MM-DD].png DATE-STAMP ALL FILES. 5. Export text response where possible (copy/paste into a doc). AFTER ALL PROMPTS: Write a 1-page summary: · X of Y prompts mention the client · Top 3 competitors appearing most frequently · 2 prompts highest priority to win (based on business value) · Patterns in which source types are being cited DONE WHEN: Baseline sheet complete. All screenshots saved and date-stamped. 1-page summary written. | ChatGPT · Gemini Advanced · Perplexity · Claude · Bing Copilot · Google Sheets · Google Drive | Depends on task 16 | Analyst | Yes — step-by-step recording needed | No | To Do
P2 | Day 5 | 18 | Strategic Alignment | Lock prompt set with written client sign-off — this is the shared scorecard | CSM emails completed prompt set Google Sheet to client. Email message: 'Please confirm this list is accurate — it is our shared scorecard for Day 30/60/90 reviews. Reply with approval to proceed.' Wait for WRITTEN sign-off (email is acceptable). Do not proceed with benchmarking until received. Log approval confirmation in Basecamp. DONE WHEN: Written sign-off received and logged in Basecamp. | Email · Google Sheets · Basecamp | Depends on task 17 | CSM | No | No | To Do
P2 | Day 5 | 19 | Strategic Alignment | Deploy ongoing prompt tracking across all 5 LLMs — set cadence, SOP, and recurring reminder | 1. In prompt tracking sheet, add 'Monthly Snapshot' tab. Freeze header row. Columns: Date ¦ Prompt ¦ AI Tool ¦ Brand Appears? ¦ Description Used ¦ Competitors Cited ¦ Source URLs ¦ Screenshot Link ¦ Notes/Changes vs Last Month 2. Set up recurring biweekly Basecamp task: 'Run GEO Prompt Check – [Client]'. Assign to: [Analyst name]. 3. Use SEMrush AI Toolkit for automated monitoring where available. Supplement with manual runs for platforms not covered by SEMrush. 4. Write 1-page GEO Measurement Plan in Google Docs: Which prompts · which AI tools · which metrics · how often · who owns each task · how results are recorded Save in /06_AI_Benchmarking. DONE WHEN: Tracking sheet live. SOP written. Recurring reminder set. Measurement plan saved. | SEMrush AI Toolkit · Google Sheets · Basecamp | Depends on task 18 | Analyst | No | No | To Do
P2 | Days 2–3 | 20 | Measurement & Analytics | Validate GA4, GSC, and Bing WMT are tracking correctly — verify commercial conversion events | GA4 VALIDATION: · Admin → Data Streams → confirm green status. · Realtime report: visit client site → you should appear within seconds. · DebugView (GTM Preview mode): trigger each conversion action on live site and confirm events fire. REQUIRED EVENTS: form_submit · phone_number_click · purchase / get-a-quote / contact · demo request · CTA clicks If NO conversion events exist: agree with client what supportive actions matter (PDF download, video play, scroll depth). Ensure tracking is in place for those actions. Log as Priority Fix in Basecamp. · Check GTM container: consent mode correctly configured · no duplicate tags · cross-domain tracking working. GSC VALIDATION: · Confirm property type (Domain property preferred over URL prefix). · Verify ownership is active (Settings → Ownership verification). · Performance → Search Results → confirm 3+ months of clicks and impressions data loads. · Note exact canonical domain being tracked. BING WEBMASTER TOOLS: · Log in at bing.com/webmasters. · If not set up: complete XML file or meta tag verification. Alert CSM immediately. · Once verified: navigate to 'AI Performance' report. Screenshot baseline data. · Sitemaps tab: confirm sitemap is submitted. Log all missing events/issues as Priority Fixes in Basecamp with owner and resolution deadline. DONE WHEN: GA4, GSC, Bing WMT all confirmed live with data. All issues logged. | GA4 · GTM Preview Mode · GSC · Bing Webmaster Tools | Depends on task 6 | Analyst | No | No | To Do
P2 | Days 3–4 | 21 | Measurement & Analytics | Export SEO performance baseline from GA4, GSC, and Bing WMT | GA4 EXPORTS: · Reports → Acquisition → Traffic Acquisition → filter 'Organic Search' → Last 12 months → Export CSV · Key Events → filter 'Organic Search' → same window → Export CSV · Identify: top 10 pages by organic traffic + top 10 pages by conversions. GSC EXPORTS: · Performance → Search Results → Last 12 months → Export CSV · Repeat with two filters: Branded queries only · Non-branded queries only · Flag pages with high impressions but CTR under 2% (near-win pages). BING WMT EXPORTS: · Reports → Search Performance → Last 6 months → Export · KEEP BING DATA SEPARATE from GSC — different audience segment. SAVE ALL FILES: · Folder: /09_Reporting/Baseline_Data/ · Filename format: [Platform]_baseline_[YYYY-MM-DD].csv DONE WHEN: All exports saved with today's date. Three page lists documented: top traffic · top conversions · low CTR. | GA4 · GSC · Bing WMT · Google Sheets | Depends on task 20 | Analyst | No | No | To Do
P2 | Days 4–5 | 22 | Measurement & Analytics | Set up GEO visibility tracking, brand mention monitoring, and build KPI dashboard | FOLDER SETUP: · Google Drive: /06_AI_Benchmarking/Monthly-Snapshots/Month-1/ · Copy Day 17 baseline screenshots and tracking sheet here. GOOGLE ALERTS: · Go to google.com/alerts · Set alerts for: client brand name · key executive names · top 3 competitors · Frequency: 'As it happens'. Send to shared team inbox. · If SEMrush Brand Monitoring available: configure for deeper unlinked mention tracking. KPI DASHBOARD (Google Looker Studio): · Create new report. Connect to GA4 + GSC properties. Note: Bing WMT data pasted in manually each month. · Include these 6 metric sections with exact definitions: 1. AI Search Health Score Formula: (Number of prompts where client appears ÷ Total prompts in set) × 100 2. AI Visibility Score Definition: Count of distinct AI platforms where client appears at least once 3. Share of Voice Formula: Client appearances ÷ (Client appearances + All competitor appearances) × 100 4. Brand Mentions Definition: Total Google Alerts hits per month (unlinked + linked) 5. Citations Definition: Number of times client URLs appear as sources in AI responses 6. Cited Pages Definition: List of specific client pages being cited in AI responses · Add Month-vs-Month comparison column to every metric so improvement is instantly visible. · Populate with Month 1 baseline data from tasks 17–21. DONE WHEN: Dashboard live. All 6 metrics have Month 1 baseline values. Google Alerts confirmed. | Google Alerts · SEMrush Brand Monitoring · Looker Studio · Google Sheets | Depends on tasks 17–21 | Analyst | No | No | To Do
P2 | Days 3–7 | 23 | Technical SEO Audit | Run full technical crawl — check HTTPS protocol, status codes, and redirects | SCREAMING FROG SETUP: · Enable JS rendering: Spider → Configuration → Rendering → JavaScript. · Configure output columns: URL · Status Code · Title · Meta Description · H1 · Canonical · Indexability · Word Count · Inlinks · Outlinks. · Run full crawl. Save crawl file to /02_Technical_Audit/[YYYY-MM-DD]_crawl. Also run SEMrush Site Audit in parallel for cross-reference. HTTPS & PROTOCOL: · Test http:// version → must redirect to https:// · Test www version → must redirect to non-www (or vice versa — whichever is canonical) · Check: both http:// AND non-www → same final canonical URL · Score in audit log: Pass / Fail / Needs Work REDIRECT HEALTH: · Screaming Frog → Response Codes → filter 301/302 · Look for chains (A→B→C) — all should be direct (A→C) · Log: Source URL ¦ Redirect chain ¦ Recommended fix STATUS CODES: · Filter for 404s → export list → note which are linked internally (these must be fixed first) · Filter for 5xx server errors → flag ALL as Critical · Confirm homepage · service pages · contact page all return 200 DUPLICATE URL / PARAMETER RISKS: · Screaming Frog → URL Parameters report · Check for: faceted navigation · session IDs · internal search pages · tag/category/archive pages · pagination · Log any parameter risks with recommended fix (canonical or noindex) AUDIT LOG COLUMNS: Issue ¦ URL(s) ¦ Severity (Critical/High/Medium/Low) ¦ Effort (Quick Fix/Needs Developer) ¦ Recommended Fix ¦ Owner DONE WHEN: Crawl file saved. All issues logged with severity and effort rating. | Screaming Frog · SEMrush Site Audit · Browser | Depends on task 6 | Analyst | No | No | To Do
P2 | Days 5–7 | 24 | Technical SEO Audit | Review crawlability, sitemaps, site architecture, rendering, and Core Web Vitals | Score each check as Pass / Fail / Needs Work in the audit log. CRAWLABILITY & ROBOTS.TXT: · Visit [domain]/robots.txt in browser · Are /services/ /blog/ /products/ blocked? → Flag as Critical if yes · Screaming Frog → Directives → Noindex → are any important pages accidentally noindexed? INDEXABILITY & CANONICALS: · Screaming Frog → Canonicals → any pages pointing to unexpected URL? · Check: /page and /page/ — are both indexable? (should be only one) · GSC → Coverage report → check 'Excluded' tab for incorrectly excluded pages XML SITEMAP: · Visit [domain]/sitemap.xml — does it load and return a 200? · GSC → Sitemaps: submitted? Any errors shown? · Bing WMT → Sitemaps: confirm submitted here too · Screaming Frog → cross-check sitemap URLs match crawlable 200-status pages only SITE ARCHITECTURE: · Screaming Frog → Crawl Depth column · Priority commercial pages must be within 3 clicks of homepage. Flag any deeper. · Manual check: are key pages in main nav AND footer? · Filter for 0 inlinks → orphan pages. Flag ALL. RENDERING: · Screaming Frog: compare rendered vs non-rendered content · Flag any headings, body sections, or CTAs that disappear without JS → Critical GEO risk CORE WEB VITALS (PageSpeed Insights — mobile mode only): · Test homepage + 2–3 priority commercial pages · Record: LCP (pass <2.5s) · INP (pass <200ms) · CLS (pass <0.1) · Flag failures as audit issues DONE WHEN: All checks complete. Every issue has Pass/Fail/Needs Work + severity + effort. | Screaming Frog · GSC · Bing WMT · PageSpeed Insights · Browser | Depends on task 23 | Analyst | No | No | To Do
P2 | Day 7 | 25 | Technical SEO Audit | Prioritise all technical findings — severity, effort, quick wins vs dev-dependent | In audit log Google Sheet, add columns: · Severity: Critical / High / Medium / Low · Effort: Quick Fix (no developer) / Needs Developer · Owner · Phase: Q-Win (Days 1–30) / Month 2 (Days 31–60) / Month 3 (Days 61–90) Sort by: Severity (Critical first) + Effort (Quick Fix first) = fix priority order. Separate into three groups: · Quick Wins: no developer, implement in Phase 3 (Days 15–24) · Medium effort: 2–4 weeks · Heavy lift / dev-dependent: Development sprint needed CSM reviews before any client delivery. DONE WHEN: Every technical issue has severity + effort + phase tag. Quick wins list isolated. | Audit log Google Sheet · Basecamp | Depends on tasks 23–24 | Analyst | No | No | To Do
P2 | Days 5–7 | 26 | Structured Data / Schema | Inventory all schema, validate core entity schema and page-level coverage | SCHEMA INVENTORY: 1. Screaming Frog → Structured Data tab → export all schema types by page 2. Cross-reference against GSC Rich Results report 3. Build schema inventory Google Sheet with columns: Page URL ¦ Schema Types Present ¦ Errors Found ¦ Priority to Fix (Critical/High/Medium/Low) ORGANISATION / LOCALBUSINESS VALIDATION: · Google Rich Results Test on homepage (search.google.com/test/rich-results) · Also use Schema.org validator · Check these fields match live content EXACTLY: name · logo URL · URL · telephone · address · email · sameAs (social profiles) · Flag any outdated addresses, old phone numbers, discontinued products PAGE-LEVEL SCHEMA COVERAGE (check each applicable page type): · Service pages → Service schema · Blog posts → Article schema (with author Person schema) · FAQ pages → FAQPage schema · Product pages → Product schema · Team/author pages → Person schema · Video content → VideoObject schema · Breadcrumbs → BreadcrumbList schema DONE WHEN: Schema inventory complete in Google Sheets. All errors logged with priority. | Screaming Frog · Google Rich Results Test · Schema.org validator | Depends on task 23 | Analyst | No | No | To Do
P2 | Days 7–10 | 27 | Structured Data / Schema | Fix broken schema, add missing schema, and evaluate Speakable for key pages | FIX ERRORS FROM TASK 26: · Work through schema inventory in priority order (Critical first) · Most fixes done via CMS plugin (Yoast / RankMath / Schema Pro) — no coding needed · After each fix: go to page → open schema plugin → update wrong field → save · Re-validate every changed page in Rich Results Test immediately ADD MISSING SCHEMA to priority pages: · Match schema type to page type (Service page → Service, blog → Article, etc.) · For Article schema: always include author Person schema SPEAKABLE SCHEMA — EVALUATE PER CLIENT: ⚠ Speakable is currently Beta per Google's own documentation. It is tied to text-to-speech/Assistant use cases, not a confirmed GEO ranking signal. Only implement if: a) Client has strong FAQ / definition / how-to content b) You have evidence Speakable is benefiting similar sites · If implementing: target 3–5 pages with clear factual answers (FAQ, definitions, how-it-works) · Add schema referencing specific section headings/paragraphs · Test each implementation in Rich Results Test LOG REMAINING UNFIXED ITEMS: · Add to Month 2 backlog in Basecamp with: URL ¦ Schema Type Needed ¦ Priority DONE WHEN: All Critical schema errors fixed. Re-tests confirm no errors on priority pages. | CMS schema plugin (Yoast / RankMath / Schema Pro) · Rich Results Test · Schema.org | Depends on task 26 | Analyst | No | No | To Do
P2 | Days 5–8 | 28 | Content Audit & Optimisation | Create full page inventory and assign priority tiers using traffic and conversion data | 1. Export full URL list from Screaming Frog. Filter by page type. 2. Build Google Sheet — 'Content Page Inventory': URL ¦ Page Type ¦ Word Count ¦ Indexable (Y/N) ¦ Schema Present (Y/N) ¦ Monthly Organic Sessions (GA4) ¦ Organic Conversions (GA4) ¦ Avg Position Google (GSC) ¦ Avg Position Bing (Bing WMT) 3. ASSIGN PRIORITY TIERS: TIER 1 — Fix first: · Pages generating leads/revenue · Pages ranking positions 5–20 in Google or Bing (near-win pages — small improvement = big traffic gain) · Pages that SHOULD appear in AI prompt answers but currently don't TIER 2 — Fix next: · High-traffic pages with low conversion rate · Thin or outdated pages with moderate traffic LOW PRIORITY: · Minimal traffic, low strategic importance 4. Save as 'Content_Page_Inventory_[YYYY-MM-DD]' in /03_Content_Audit. DONE WHEN: All pages listed with data. Priority tiers assigned. Top 15–20 pages confirmed for detailed review. | Screaming Frog · GA4 · GSC · Bing WMT · CMS · Google Sheets | Depends on tasks 20–21 | Analyst | No | No | To Do
P2 | Days 7–9 | 29 | Content Audit & Optimisation | Review metadata, content quality, and page clarity across all Tier 1 pages | METADATA (Screaming Frog → Page Titles / Meta Descriptions / H1 tabs): · Title tag: unique? Under 60 chars? States the topic AND who it's for? · Meta description: under 160 chars? Compelling reason to click? · H1: exactly ONE per page? Specific and relevant to page topic? CONTENT QUALITY (manual review in browser — score each page 1–3): Score 1–3 on: Depth (1=thin, 3=comprehensive) · Freshness (1=outdated, 3=current) · Uniqueness (1=generic/duplicate, 3=distinctive) Flag as thin: · Under 300 words on a commercial/service page · Under 400 words on an informational page Flag as generic: · Copy starting with 'We are a leading provider of…' · No specific proof, examples, or differentiators Flag as outdated: · Wrong year, old stats, discontinued products or services mentioned PAGE CLARITY CHECK — apply Page Clarity Checklist (score Pass/Fail per criterion): □ Does the page explain what it's about within the first paragraph? □ Does the opening answer the core buyer question directly? □ Are buyer questions answered on the page? □ Is there a clear, specific CTA? □ Are there internal links to related pages? LOG ALL ISSUES: Page URL ¦ Issue Type ¦ Current State ¦ Recommended Fix ¦ Priority ¦ Score (1–3 where applicable) DONE WHEN: Every Tier 1 page reviewed. All issues logged with scores. | Screaming Frog · Browser · CMS · Google Sheets | Depends on task 28 | Analyst | No | No | To Do
P2 | Days 8–10 | 30 | Content Audit & Optimisation | Rewrite metadata, restructure headings, add FAQ sections, and fix on-page elements | METADATA REWRITES (GEO-optimised format): · Title = [Primary Entity] ¦ [Differentiator] ¦ [Brand Name] Under 60 chars. Front-load the most important words. Example: 'Cloud Security for Mid-Market Finance Teams ¦ Clearpath' · Meta description = direct answer to core intent + soft CTA. Under 160 chars. Example: 'See how Clearpath reduces breach risk for finance teams. Learn how it works →' · Implement in CMS. Use bulk editor if available. IMAGE ALT TEXT: · Check all images on Tier 1 pages. Alt text must describe the image naturally. Bad: 'image001' ¦ Good: 'Cloud dashboard showing live threat monitoring' INTERNAL LINKS: · Each Tier 1 page should link to at least 2–3 other relevant pages. · Anchor text must be descriptive — never generic. Bad: 'click here' ¦ Good: 'See our managed security services' HEADING RESTRUCTURE: · Rewrite vague H2/H3s to questions or numbered formats: Before: 'Our Services' → After: 'What services does [Company] offer?' Before: 'Benefits' → After: '5 key benefits of [service] for [audience]' Before: 'Process' → After: 'How does [service] work? (3 steps)' · Restructure H1–H6 as questions or direct answers where appropriate. FAQ SECTIONS: · Add to every Tier 1 page that lacks one. · Source questions from: kickoff notes · Google PAA box · target prompt set (task 16). · Write 4–8 FAQs per page. Use natural language — exactly how someone types into an AI tool. · Apply FAQPage schema to every FAQ section. ANSWER-FIRST INTRO PARAGRAPH: · Rewrite opening paragraph of each priority page. · First 2–3 sentences must answer the core question directly. · Supporting detail follows. Do not bury the answer. Example: Page about cloud security → open with what cloud security is and why it matters for [audience], before expanding into features. DONE WHEN: All Tier 1 pages have updated metadata, alt text, internal links, restructured headings, FAQ sections, and answer-first intros. | CMS · Google Search (PAA) · SEMrush · Screaming Frog | Depends on task 29 | Analyst + Content Lead | No | Yes | To Do
P2 | Day 10 | 31 | Content Audit & Optimisation | Flag thin pages and categorise all content issues into a prioritised backlog | FIND THIN PAGES: · Screaming Frog → Readability tab → filter pages under 400 words (informational) or 300 words (commercial). · For each thin page decide one action: Expand — important page, needs more depth Merge — consolidate with a related page Delete/Noindex — not needed THIN CONTENT ACTION LIST (Google Sheet): Page URL ¦ Word Count ¦ Page Type ¦ Action (expand/merge/delete) ¦ Priority CATEGORISE ALL CONTENT ISSUES from review log (task 29): · Metadata — titles, meta descriptions, H1s · Structure — headings, FAQs, formatting · Quality — thin, outdated, generic copy · Trust — missing proof, no CTA, no author bio · GEO-specific — not answer-ready, missing extractable facts, no FAQs TAG EACH ITEM: · Quick Fix (no developer needed, done in Days 15–24) · Month 2 task · Developer-dependent DONE WHEN: Thin content list documented. All content issues categorised and tagged. | Screaming Frog · Google Sheets | Depends on task 29 | Analyst | No | No | To Do
P2 | Days 7–10 | 32 | GEO Readiness | Audit site for AI readability — brand clarity, content structure, extractable elements | BRAND CLARITY CHECK (homepage — within first scroll): Score Pass/Fail/Needs Work: □ What does this company do? — clear within 10 seconds □ Who is it for? — stated explicitly □ Why is it different? — a real differentiator, not 'leading provider' Check same criteria on all Tier 1 service/product pages. OFFERING CLARITY (service/product pages): For each page, check: simple language · who it's for · when to use it · how it works · what happens next TERMINOLOGY CONSISTENCY: · Use Screaming Frog Search tab to search for each core offering name across the site · Flag inconsistencies: same product called different things in menus vs headings vs URLs vs body copy vs schema ANSWER-FIRST FORMATTING: · First 100 words answer the core question — not vague intro · Content in short, scannable blocks · Supporting detail follows direct answer EXTRACTABLE CONTENT ELEMENTS (check per page — log Present/Missing): □ Factual statements with specifics (not 'many years of experience') □ Definitions of key terms □ Step-by-step how-it-works sections □ FAQ sections □ Comparison-style content ('X vs Y', 'The difference between A and B') □ Numbered lists and structured tables SEMRUSH AI TOOLKIT: · Run analysis for client domain + top 3 competitors · Export: share of voice · sentiment score · competitor citation list · Save to /05_GEO_Readiness/SEMrush_AI_Baseline_[YYYY-MM-DD] DONE WHEN: GEO readiness scored per page. All extractable gaps documented. SEMrush AI report saved. | Browser · Screaming Frog · SEMrush AI Toolkit · Mridul's GEO tools | Depends on task 29 | Analyst | No | No | To Do
P2 | Days 7–10 | 33 | Brand Narrative | Create the brand source-of-truth document — single approved reference for all GEO work | Create Google Doc: '[Client Name] – Brand Source of Truth' Share with: all writers · strategists · implementers · approvers Do NOT proceed with content changes in Month 2 until this document has client sign-off. SECTION 1 — Company Descriptions (client sign-off required on both): · 25-word version: for schema and AI answers — 1 clean, specific sentence · 75-word version: for About pages and press — 3–5 sentences Good: 'B2B SaaS cybersecurity platform for mid-market finance teams' Bad: 'tech company' SECTION 2 — Category labels: · How should AI describe what category this business is in? · 2–3 specific category labels the brand should own SECTION 3 — Service/product naming rules: Approved Full Name ¦ Acceptable Short Name ¦ Forbidden Variations (e.g. 'Managed Detection & Response' ¦ 'MDR' ¦ Never: 'managed security') SECTION 4 — Target audience labels and pain point descriptions SECTION 5 — Approved differentiators + evidence behind each: Differentiator ¦ Supporting Evidence ¦ Claim Status (Approved / Needs sign-off) SECTION 6 — Tone rules: · 3 things to always do · 3 things to never say SECTION 7 — Claims requiring compliance approval before publishing SECTION 8 — AI Description Brief: Write 3–5 preferred 'AI answer paragraphs' — what the ideal AI-generated summary of the brand should look like. Frame as instructions: 'When describing [Company], always mention X. Emphasise Y. Never describe as Z.' Obtain written client sign-off before Month 2 work begins. DONE WHEN: Document complete. Client-approved. Saved in /01_Strategy. All contributors confirmed receipt. | Google Docs · Kickoff notes · Differentiator table | Depends on tasks 10–14 | CSM + Senior Analyst | No | No | To Do
P2 | Days 8–12 | 34 | Trust & Proof | Audit all trust signals, GBP, review platforms, Wikipedia/Wikidata, and identify gaps | COMPANY-LEVEL TRUST (score Pass/Fail/Needs Work): □ About page — complete, not generic □ Contact page — real address, phone number, email □ Legal entity name visible □ Privacy Policy □ Terms & Conditions □ Cookie policy (where required) EXPERTISE & AUTHORSHIP: □ Named authors on ALL blog posts (not 'Admin') □ Author bios with: credentials · experience · qualifications · media appearances □ Team or Experts page with names and photos □ Person schema on author/team pages PROOF ON COMMERCIAL PAGES (review each priority commercial page): □ Testimonials □ Case studies with quantified results ('Reduced costs by 35%' NOT 'great results') □ Client logos □ Certifications and awards □ For each major differentiator: is there a linked source, data point, or verifiable case study? Flag any unsupported claims as medium-priority fixes. GOOGLE BUSINESS PROFILE: · Log in at business.google.com · Check: description complete (using brand SOT language) · correct primary + secondary categories · Q&A answered · at least one post in last 30 days · photos uploaded · Flag incomplete fields as Basecamp to-dos assigned to CSM REVIEW PLATFORMS: · Do NOT default to creating Trustpilot immediately · First: run brand mentions search (task 38) to identify which platforms already include brand reviews · Then: check which platforms appear in AI citation results for your category (run target prompts and note which review platforms are cited) · For each active platform (Google, Trustpilot, G2, Capterra, Clutch, Yelp): ✓ Profile claimed · ✓ Description complete (using brand SOT language) · ✓ All recent unanswered reviews have responses · Create profiles only on HIGH-INFLUENCE platforms where brand is absent WIKIPEDIA / WIKIDATA (LLMs draw heavily from these sources): · Search Wikipedia for brand name AND key executives · Check Wikidata at wikidata.org for entity record accuracy (name, description, founding date, HQ, website) · Log current status: Present / Absent / Inaccurate · Flag as off-site priority if AI competitors are cited via Wikipedia but client has no entry LOG MISSING TRUST ASSETS: Page URL ¦ Missing Element (bio/case study/certification/proof block) ¦ Recommended Action ¦ Priority Add to Month 2 backlog in Basecamp. DONE WHEN: Trust audit complete. GBP updated. Review responses drafted and sent to client for approval. | Browser · GBP · Trustpilot · G2 · Capterra · Wikipedia · Wikidata | Depends on task 33 | Analyst + CSM | No | No | To Do
P2 | Days 10–11 | 35 | Internal Linking | Review internal linking structure, find orphan pages, and build improvement list | UNDER-LINKED PRIORITY PAGES: · Screaming Frog → Inlinks tab · Any Tier 1 page with fewer than 3 inbound internal links → flag immediately ORPHAN PAGES: · Screaming Frog → filter pages with 0 inlinks · Flag ALL — these are invisible to crawlers AND AI scrapers NAVIGATION AND FOOTER EXPOSURE: · Manually check: is each Tier 1 page in main nav or footer? · Any that aren't → flag for navigation review in Month 2 CROSS-LINKING BETWEEN PAGE TYPES: · Open 5 blog posts: do they link to relevant commercial/service pages? · Open 5 service pages: do they link to related case studies? · Open case study pages: do they link back to core solution pages? · Open industry pages: do they link to related offerings? ANCHOR TEXT QUALITY: · Review anchor text on internal links to Tier 1 pages Bad: 'click here' / 'learn more' / 'read more' Good: 'See our managed security services' / 'Read the [Client] cloud migration case study' SITE ARCHITECTURE: · Map top 2 levels of site navigation in Google Sheet · Cross-reference against page inventory — are key commercial pages in the nav or buried? · Identify missing hub/pillar/category pages IMPROVEMENT LIST (Google Sheet): Source Page ¦ Destination Page ¦ Recommended Anchor Text ¦ Priority ¦ Notes Add Month 2 fixes to Basecamp backlog. DONE WHEN: Linking audit complete. Improvement list saved. Orphan pages and under-linked pages identified. | Screaming Frog · Browser · Google Sheets | Depends on tasks 23–28 | Analyst | No | No | To Do
P2 | Days 5–8 | 36 | AI Benchmarking | Run structured AI tests for client and competitors across all 5 LLMs — record everything | CONFIRM PROMPT SET (task 16) covers all 5 types: Branded · Non-branded · Comparison · Problem-solution · Buyer-intent CLIENT AI TEST — for every prompt × every tool: TRACKING SHEET COLUMNS: Prompt ¦ AI Tool ¦ Brand Appears? (Y/N) ¦ Exact Description Used ¦ All Cited URLs ¦ Competitors Mentioned ¦ Response Format (list/prose/table/none) ¦ Platform-Specific Notes COMPETITOR AI TEST: · Run SAME prompts for each competitor. Add competitor columns to same tracking sheet. · Note: which competitors appear per platform · how they are framed · where they are stronger than client NARRATIVE ACCURACY: · Compare ALL AI-generated descriptions of the client against Brand Source-of-Truth doc (task 33) · Flag any inaccuracies · Identify which source URLs are driving the current narrative — own site vs third-party SOURCE PATTERNS: · Review tracking sheet for patterns: which source types appear most? (own site / press / directories / review sites) · Which prompts is the brand absent from entirely? · What response format do AI tools favour? (list vs prose vs no result) ARCHIVE ALL EVIDENCE: · Screenshots → /06_AI_Benchmarking/Month-1-Evidence/[Platform]/[Prompt-slug]_[YYYY-MM-DD].png · Date-stamp everything. Organise by platform, then prompt. WRITE 1-PAGE INSIGHT NOTE: · Top 3 reasons competitors outperform client in AI visibility · Patterns in source types being cited CITATION GAPS: · Identify top 3 authoritative sources where competitors appear but client doesn't · These become Month 2 outreach targets DONE WHEN: All prompts run for client and competitors. Screenshots saved and date-stamped. Insight note written. Citation gaps identified. | ChatGPT · Gemini Advanced · Perplexity · Claude · Bing Copilot · Google Sheets · Google Drive | Depends on tasks 17–18 | Analyst | No | No | To Do
P2 | Days 8–11 | 37 | Competitor Review | Systematically review top 3–5 competitors for AI retrieval readiness and citation gaps | For top 3–5 competitors review and score in Competitor Analysis Google Sheet: CLARITY AND POSITIONING (score each 1–3): · Offering clarity: 1=vague, 2=clear, 3=highly specific with examples · Audience clarity: 1=generic, 2=identified, 3=named with pain points · Differentiator clarity: 1=generic claims, 2=some proof, 3=specific evidence CONTENT FOR AI RETRIEVAL (check per competitor — log Present/Absent): □ FAQ sections □ Definition blocks □ Comparison tables / 'X vs Y' content □ Numbered lists and how-it-works steps □ Summary paragraphs at page top □ Answer-first openings TRUST AND PROOF: □ Named experts / team page □ Dedicated case study pages □ Certifications and awards □ Testimonials with specifics □ Social proof elements BREADTH AND CORROBORATION: · Run full target prompt set with each competitor brand as subject · Record how often each appears and which third-party sources cite them COMPETITOR ADVANTAGE SUMMARY (1-page doc): Write a summary with these two sections: 1. Top 3 competitor strengths (what they do better than client) 2. Gap map: where client underperforms vs competitors on: Clarity ¦ Content Structure ¦ Proof/Trust ¦ AI Retrieval Readiness CITATION GAP LOG: Log top 3 sources that cite competitors but NOT the client: Source Name ¦ URL ¦ Why They Cite Competitors ¦ Recommended Action for 60-day phase DONE WHEN: Competitor analysis sheet complete with 1–3 scores. Advantage summary written. Citation gap log saved. | Browser · SEMrush · ChatGPT · Perplexity · Google Sheets | Depends on task 36 | Analyst | No | No | To Do
P2 | Days 10–14 | 38 | Brand Signals & Off-Site | Map brand mention baseline, NAP consistency, source influence, and platform opportunities | BRAND MENTION BASELINE: · SEMrush Brand Monitoring: export all unlinked mentions. Log total count and top source types. · Also: Google search for brand name without quotes, review pages 1–3 of results. · This count is the Month 1 baseline. Log in /09_Reporting/Baseline_Data. NAP CONSISTENCY (Name, Address, Phone): Check across these specific sources: 1. Google Business Profile 2. Homepage footer 3. Schema markup (check in Screaming Frog) 4. Wikipedia (if present) 5. Wikidata 6. Yelp 7. Bing Places 8. Apple Maps 9. Yellow Pages 10. One sector-specific directory Log discrepancies in NAP Audit Google Sheet: Source ¦ Name (Recorded) ¦ Address (Recorded) ¦ Phone (Recorded) ¦ Match? (Y/N) ¦ Fix Required Flag even small discrepancies: abbreviations · old phone numbers · old addresses · punctuation differences in business name. SOURCE INFLUENCE MAPPING: · Review AI benchmark results and competitor citation data (tasks 36–37) · Identify publishers, directories, and platforms that appear most often as AI sources · Build ranked influence source list: Source Name ¦ URL ¦ Type (directory/publisher/review/forum) ¦ Competitor Present? (Y/N) ¦ Client Present? (Y/N) PLATFORM OPPORTUNITY MAP: Platform ¦ Competitor Present? (Y/N) ¦ Client Present? (Y/N) ¦ Quality of Client Presence ¦ Effort to Improve ¦ Priority Platforms to check: Reddit (relevant subreddits) · YouTube · LinkedIn · sector forums · industry directories DRAFT OFF-SITE PLATFORM STRATEGY (1-page doc): For each of top 3 priority platforms define: · Objective · Content approach · Frequency · Owner for 60-day phase Save in /01_Strategy. DONE WHEN: Mention baseline recorded. NAP discrepancies logged. Platform opportunity map complete. Platform strategy drafted. | SEMrush Brand Monitoring · Google Alerts · Browser · Google Sheets | Depends on task 36 | Analyst | No | No | To Do
PHASE 3 Days 15–24 Quick Wins Implementation
P3 | Days 15–24 | QW-T1 | Quick Wins Implementation | Fix redirect chains and broken links from technical audit | From task 23 export: filter for redirect chains (3+ hops) and 4xx errors. Fix redirect chains in CMS or .htaccess so all redirect directly (A→C, not A→B→C). Fix or redirect broken 4xx pages that are internally linked. Re-crawl in Screaming Frog after each batch of fixes to confirm resolution. DONE WHEN: No redirect chains. No internally-linked 4xx errors remain. | Screaming Frog · CMS / .htaccess | Depends on task 23 findings | Analyst + Dev | No | Yes | To Do
P3 | Days 15–24 | QW-T2 | Quick Wins Implementation | Submit updated XML sitemap to GSC and Bing WMT | Update sitemap to include ONLY indexable 200-status pages. Remove any noindexed, redirected, or 4xx pages from sitemap. Upload to GSC → Sitemaps section. Upload to Bing WMT → Sitemaps section. Confirm no errors on either platform. DONE WHEN: Updated sitemap live. No errors in GSC or Bing WMT sitemaps. | CMS sitemap plugin · GSC · Bing WMT | Depends on task 24 | Analyst | No | Yes | To Do
P3 | Days 15–24 | QW-T3 | Quick Wins Implementation | Fix accidental noindex tags on important pages | From task 24 audit: identify priority pages with incorrect noindex tags. Update meta robots tags in CMS to remove noindex. Verify fix using GSC URL Inspection tool after publishing. DONE WHEN: All priority pages return correct indexable status in GSC URL Inspection. | CMS · GSC URL Inspection | Depends on task 24 | Analyst | No | Yes | To Do
P3 | Days 15–24 | QW-S1 | Quick Wins Implementation | Implement Organisation/LocalBusiness schema fixes on homepage | Update JSON-LD in homepage template: Fix: name · logo URL · URL · telephone · address (full postal) · email · sameAs (all social profiles) Validate in Rich Results Test BEFORE publishing. Confirm all fields match live content exactly — no outdated information. DONE WHEN: Rich Results Test shows no errors on homepage schema. | CMS · Rich Results Test | Depends on task 26 | Analyst | No | Yes | To Do
P3 | Days 15–24 | QW-S2 | Quick Wins Implementation | Add missing FAQ schema to top informational and commercial pages | Add FAQPage JSON-LD to pages where FAQ content was added in task 30. Test each page in Rich Results Test after adding. Confirm FAQ schema and FAQ content match exactly. DONE WHEN: All FAQ pages with content also have validated FAQ schema. | CMS · FAQ schema plugin · Rich Results Test | Depends on task 30 | Analyst | No | Yes | To Do
P3 | Days 15–24 | QW-C1 | Quick Wins Implementation | Publish updated metadata for top 20 priority pages | Implement rewritten title tags and meta descriptions from task 30 in CMS. Use bulk editor if CMS supports it. Check each page renders title correctly after publishing (view in browser tab). DONE WHEN: All 20 priority pages show updated metadata in browser and Screaming Frog re-crawl. | CMS metadata editor · Screaming Frog | Depends on task 30 | Analyst | No | Yes | To Do
P3 | Days 15–24 | QW-C2 | Quick Wins Implementation | Restructure headings on priority informational pages to question or numbered format | Implement heading rewrites from task 30 in CMS. Check page renders correctly after publishing — no broken layout. Verify H1 is still exactly one per page. DONE WHEN: All priority informational pages have question-led or numbered H2/H3 headings. | CMS | Depends on task 30 | Analyst + Content Lead | No | Yes | To Do
P3 | Days 15–24 | QW-C3 | Quick Wins Implementation | Publish FAQ blocks on top 5 commercial and informational pages | Implement FAQ content and FAQPage schema from task 30 on top 5 pages. Review formatting before publishing — questions and answers must display cleanly. Confirm schema validates in Rich Results Test after publishing. DONE WHEN: FAQ blocks live on 5 pages. Schema validated on all. | CMS · FAQ schema plugin · Rich Results Test | Depends on task 30 | Analyst + Content Lead | No | Yes | To Do
P3 | Days 15–24 | QW-C4 | Quick Wins Implementation | Add answer-first summary paragraphs to top 5 informational pages | Write a 2–3 sentence answer-first intro for each page based on GEO readiness review (task 32). The intro must: answer the core question directly in the first sentence · be placed above the fold · not be a vague marketing statement. Implement in CMS above all other body content. Example: For a page on cloud security: 'Cloud security refers to the tools and policies that protect data, apps, and infrastructure hosted in the cloud. It is essential for any business storing sensitive customer or financial data online. [Company] provides [specific solution] for [specific audience].' DONE WHEN: Answer-first intro live on 5 pages. Each intro is 2–3 sentences and answers the core question. | CMS | Depends on task 32 | Content Lead | No | Yes | To Do
P3 | Days 15–24 | QW-C5 | Quick Wins Implementation | Add internal links from high-traffic blog posts to priority commercial pages | From task 35 linking audit: identify the top 5 blog posts with the most organic traffic that have NO link to commercial/service pages. For each blog: find a natural contextual opportunity to add a link. Anchor text must be descriptive and specific. Bad: 'click here' / 'learn more' Good: 'See how [Company] delivers [service]' / 'Read our [specific service] guide' Implement in CMS. DONE WHEN: 5 blogs updated with contextual links to priority commercial pages. | CMS | Depends on task 35 | Analyst + Content Lead | No | Yes | To Do
P3 | Days 15–24 | QW-TR1 | Quick Wins Implementation | Update GBP profile with complete description, categories, and publish a fresh post | In Google Business Profile (business.google.com): · Update description using language from Brand Source-of-Truth doc (task 33) · Add/confirm all relevant primary AND secondary categories · Answer any unanswered Q&A questions · Publish at least one post (tip, update, or offer) · Confirm all photos are current and high quality Note: GBP is a direct entity-resolution input for Google AI Overviews. Complete profiles improve AI citation accuracy. DONE WHEN: GBP description updated. Categories confirmed. Post published. Q&A answered. | Google Business Profile | Depends on task 34 | CSM | No | Yes | To Do
P3 | Days 15–24 | QW-TR2 | Quick Wins Implementation | Respond to all unanswered reviews on Google and active review platforms | Clear the unanswered review queue from task 34 findings. Use brand tone from Brand Source-of-Truth doc (task 33) — no generic responses. For negative reviews: acknowledge the concern · offer to resolve · do not be defensive. For positive reviews: thank specifically for what they mentioned · reinforce a differentiator. Route all drafted responses to client for approval BEFORE posting. DONE WHEN: Zero unanswered reviews on all active platforms. | GBP · Trustpilot · G2 · Capterra | Depends on task 34 | CSM | No | Yes | To Do
P3 | Days 15–24 | QW-TR3 | Quick Wins Implementation | Fix NAP inconsistencies in top 10 priority directories | From task 38 NAP audit: identify the highest-priority mismatches (any discrepancy in name, address, or phone). Update the top 10 directories from the NAP audit list. Document each correction: Directory ¦ Old Value ¦ New Value ¦ Date Corrected Update the NAP Audit Google Sheet to mark corrections as done. DONE WHEN: Top 10 directory listings match GBP exactly. Corrections documented. | Directory profiles · NAP Audit sheet | Depends on task 38 | Analyst | No | Yes | To Do
PHASE 4 Days 25–30 Consolidation & Client Handoff
P4 | Days 25–27 | 39 | Reporting & Action Planning | Consolidate all findings into one master backlog — score, deduplicate, and prioritise | 1. BUILD MASTER BACKLOG GOOGLE SHEET: Merge all open items from: audit log (task 23–25) · content review (task 29–31) · schema inventory (task 26) · trust audit (task 34) · linking list (task 35) · AI benchmarking (task 36) · competitor review (task 37) · off-site findings (task 38) 2. REMOVE DUPLICATES: Delete any issue appearing in more than one source list. 3. TAG EACH ITEM: Category: Technical ¦ Content ¦ Schema ¦ Trust ¦ GEO ¦ Measurement 4. SCORE EACH ITEM: Impact: H (high) / M (medium) / L (low) Effort: H (heavy) / M (medium) / L (light — quick fix) Priority Score = Impact × Effort (inverse — high impact + low effort = highest priority) Phase Tag: Q-Win (Days 1–30) ¦ Month 2 (Days 31–60) ¦ Month 3 (Days 61–90) 5. CONTENT GAP LIST — add as a SEPARATE tab in the backlog sheet: Columns: Topic ¦ Content Type (comparison / definition / case study / FAQ hub) ¦ Target Prompt(s) it must answer ¦ Priority Source from: prompt set gaps (task 17) · competitor content audit (task 37) · thin page list (task 31) DONE WHEN: Master backlog complete. Every item has category + impact + effort + phase tag. Content gap tab populated. | Google Sheets · Basecamp | All audit tasks complete (tasks 23–38) | Analyst | No | No | To Do
P4 | Days 25–27 | 40 | Reporting & Action Planning | Define Month 2 implementation priorities — build sprint plan in 4 weekly workstreams | CSM and analyst review prioritised backlog (task 39) together. BUILD MONTH 2 SPRINT PLAN in Google Docs: Organise into 4 weekly workstreams: WEEK 1 (Days 31–37): Technical fixes + critical schema WEEK 2 (Days 38–44): Content rewrites (priority pages) WEEK 3 (Days 45–51): New content production (gap pages) + trust additions WEEK 4 (Days 52–60): Internal linking + off-site activation + mid-cycle benchmark For each task in the plan: Task ¦ Category ¦ Owner ¦ Effort estimate ¦ Done-when criteria Log Month 2 tasks as Basecamp to-dos with assigned owners and due dates. POPULATE REPORTING TEMPLATE: · Looker Studio (or agreed format) with all baseline data from Days 1–14. · Confirm tracking owner and update frequency for each KPI. · CSM reviews before sharing with client. DONE WHEN: Month 2 sprint plan structured into 4 weeks. Reporting template populated. CSM sign-off on plan. | Google Docs · Google Sheets · Looker Studio · Basecamp | Depends on task 39 | CSM + Analyst | No | No | To Do
P4 | Day 25 | 41 | Reporting & Action Planning | Internal review of Month 1 outputs with CSM, delivery team, and leadership | CSM schedules 60-min internal review in Google Meet. Attendees: CSM · delivery lead · senior reviewer / leadership. AGENDA: 1. Key findings summary (technical · content · schema · trust · GEO readiness · AI benchmarking) 2. Quick wins delivered in Phase 3 — what was implemented and what changed 3. KPI baselines — all 6 metrics from Looker Studio dashboard 4. Month 2 priorities — walk through sprint plan 5. Risks and blockers — anything that could delay Month 2 Analyst prepares a summary doc or Basecamp message before the call. Internal sign-off documented in Basecamp before client delivery. DONE WHEN: Internal sign-off received and logged in Basecamp. | Google Meet · Basecamp · Looker Studio | Depends on tasks 39–40 | CSM | No | No | To Do
P4 | Days 28–30 | 42 | Reporting & Action Planning | Set 60-day expectations with client and deliver the complete 30-Day Output Pack | SET EXPECTATIONS (in biweekly client sync): Frame Month 1 clearly: 'Month 1 = the full audit and foundation phase. From Day 31, implementation begins — this is when GEO visibility improvements compound.' Do NOT present Month 1 as an implementation phase. Frame it as discovery and foundation. 30-DAY OUTPUT PACK (compile in /10_Client_Deliverables): Send to client 48 hrs BEFORE the readout call. Pack contents (all 7 items required): 1. GEO vs SEO Mapping Document What it contains: How GEO complements (not replaces) SEO · which signals overlap · what GEO adds that SEO alone cannot achieve · how the two strategies reinforce each other 2. Top 10 Quick Wins List — immediately actionable items with effort estimates 3. Audit Summary (one doc covering all workstreams): Technical findings · Content gaps · Schema status · Trust gaps · GEO readiness scores · AI benchmarking results 4. Month 1 AI Evidence Pack: Prompt set (signed off) · All baseline screenshots organised by platform · 1-page summary doc 5. Brand Source-of-Truth Document (approved version) 6. KPI Baseline Dashboard link (Looker Studio) — all 6 metrics with Month 1 values 7. Month 2 Implementation Roadmap (sprint plan with 4 weekly workstreams) READOUT CALL (60 min): Book via Google Meet. Attend: CSM · delivery lead · client contacts. Walk through pack. Answer questions. WRITTEN SIGN-OFF: Get written approval on Month 2 roadmap (email is sufficient) BEFORE any implementation work begins. DONE WHEN: All 7 pack items delivered. Readout call booked. Month 2 roadmap has written sign-off. | Google Meet · Google Drive · Email · Looker Studio | Depends on task 41 | CSM | No | No | To Do
LEGEND: Phase colours: P1=Navy · P2=Green · P3=Brown · P4=Purple ¦ Quick Win=deliverable within Days 1–30 without developer ¦ Training Req=yellow=upskilling needed ¦ Status: To Do / In Progress / Done ¦ Scoring: content 1–3 (1=poor, 3=strong) · competitor 1–3 · Pass/Fail/Needs Work for audits